## SWOT analysis
SWOT
Objective: Cybersecurity risk management
Strengths (Internal, Positive factors) | Weaknesses( Internal, Negative factors) | Opportunities(External, positive factors) | Threats(External, negative factors)
Robust Security Policies | Lack of Employee Awareness | AI-driven threat detection | Increasing Cyber threats
Advanced Threat Protection | Unpatched softwares and legacy systems | Cloud Security Enhancements | Zero-day Vulnerabilities
Regular Security Training | Weak access controls policies | Compliance as a competitive advantage | Third-Party Vendor Risks
Data Encryption (AES-256) | Slow incident response time | Cyber Insurance | Regulatory compliance changes
Multi-Factor Authentication(MFA) | Limited Budget for Cybersecurity controls | Public-Private Partnerships | Sophisticated Insider Threats
Incident Response Plan | Decentralized IT security management | Automation of security processes | Social Engineering attacks
Compliance with Regulatory Standards | No SIEM Systems | Investment in managed security services | IoT Security Risks
Cloud Security Measures | BYOD Risks | User Behaviour Analytics | Cloud Security Breaches
Regular Security Audits | Weak vendor risk management | Integration of DevsecOps | Cyber Warfare& Nation-State Attacks

## SWOT
SWOT Analysis
Objective: SWOT analysis for a successful startup
Strengths( Internal, Positive) | Weakness( Internal, Negative) | Opportunities(External, Positive) | Threats(External, Negative)
Innovative product/ service | Limited Financial resources | Market growth & Demand | Intense competition
Strong leadership & Vision | Scalability challenges | Strategic partnerships | Regulatory changes
Agile & Adaptable | Brand recognition | Global expansion | Economic downtime
Tech-driven efficiency | High burn rate | Technological advancements | Cybersecurity Risk
Customer-centric approach | Dependency on key personnel | Government incentives | Talent acquisition & Retention
Efficient cost mangement | Lack of established processes | Shifting consumer behaviour | Changing market trends

## Sheet1
Risk Description | Risk score | Risk Score | Risk Priortization | Risk Description
Limited Financial resources | 20 | 20 | Medium High | Economic downtime
Scalability challenges | 8 | 20 | Medium High | Limited Financial resources
Brand recognition | 15 | 15 | Medium | Talent acquisition & Retention
High burn rate | 6 | 15 | Medium | Brand recognition
Dependency on key personnel | 8 | 12 | Medium | Regulatory changes
Lack of established processes | 1 | 12 | Medium | Cybersecurity Risk
Intense competition | 8 | 8 | Low Medium | Scalability challenges
Regulatory changes | 12 | 8 | Low Medium | Intense competition
Economic downtime | 20 | 8 | Low Medium | Dependency on key personnel
Cybersecurity Risk | 12 | 6 | Low Medium | High burn rate
Talent acquisition & Retention | 15 | 3 | Low | Changing market trends
Changing market trends | 3 | 1 | Low | Lack of established processes

## 3X3 Matrix
Risk analysis Table
Impact
Likelihood | Low(1) | Medium(2) | High(3)
High(3) | 3 | 6 | 9
Medium(2) | 2 | 4 | 6 | Risk score= Likelihood x Impact
Low(1) | 1 | 2 | 3
Color Coding
7-9 | High
4-6 | Medium
1-3 | Low
Risk Matrix
Impact
Likelihood | Low(1) | Medium(2) | High(3)
High(3) | Low | Medium | High
Medium(2) | Low | Medium | Medium
Low(1) | Low | Low | Low

## 5X5 matrix
Risk analysis Table
Impact
Likelihood | Insignificant(1) | Minor(2) | Moderate(3) | Major(4) | Critical(5)
Rare(1) | 1 | 2 | 3 | 4 | 5
Unlikely(2) | 2 | 4 | 6 | 8 | 10
Possible(3) | 3 | 6 | 9 | 12 | 15
Likely(4) | 4 | 8 | 12 | 16 | 20
Almost certain(5) | 5 | 10 | 15 | 20 | 25
Color Coding
1-5 | Low
6-10 | Low Medium
11-15 | Medium
16-20 | Medium High
21-25 | High
Risk Matrix
Impact
Likelihood | Insignificant(1) | Minor(2) | Moderate(3) | Major(4) | Critical(5)
Rare(1) | Low | Low | Low | Low | Low
Unlikely(2) | Low | Low | Low Medium | Low Medium | Low Medium
Possible(3) | Low | Low Medium | Low Medium | Medium | Medium
Likely(4) | Low | Low Medium | Medium | Medium High | Medium High
Almost certain(5) | Low | Low Medium | Medium | Medium High | High

## Risk Register
Risk ID | Risk description | Risk category | Asset affected | Threat source | Likelihood | Impact | Risk score | Existing controls | Risk Treatment | Owner | Status | Timeline | Review date
R001 | Weak Password policy | Cybersecurity | User accounts | Insider Threat | 4(High) | 5(critical) | 20(High) | Password policy, MFA | Enforce stronger password policies & MFA | IT security team | Open | 15 days | 2025-04-14 | DD-MM-YYYY
R002 | Legacy system vulnerabilities | IT infrasructure | Entire organisation | Hackers/ Exploits | 2(Low) | 5(critical) | 10(Medium) | patch management | Upgrade the legacy system, endpoint security | IT Manager | Under review | 30 days | 2025-05-01 | MM-DD-YYYY
R003 | System downtime | Operational | ERP System | Hardware failure | 4(high) | 3(medium) | 12(medium) | Backup servers, cloud DR | Implement auto-failover | IT Team | In progress | 24-48 hrs | 2025-03-31 | April 01 -25
R004 | GDPR Non-compliance | Compliance | Customer data | Data breach | 5(critical) | 5(critical) | 25(critical) | DLP, Data encryption | Conduct compliance audits regularly | Compliance officer | Open | 5 days | 2025-04-01
R005 | Negative media coverage | Reputational | Brand reputation | Social media attack | 3(medium) | 5(critical) | 15(high) | PR Crisis plan | Social media monitoring & response plan | PR Team | Open | 24 hrs | 2025-04-28
R006 | Vendor data breach | Supply chain ( Third party risk) | Third party vendors | cyber attack | 3(medium) | 4(high) | 12(medium) | vendor security review | Implement vendor risk management | Procurement | Open | 7 days | 2025-04-04
R007 | Natural disaster affecting operations | Environmental | Data centers | Earthquake/ floods | 1(low) | 5(critical) | 5(low) | disaster recovery plan | relocate backup servers to a safe zone | Facilities Team | Open | 7 days | 2025-04-04
R008 | Competitor gaining market share | Strategic | company revenue | Market disruption | 4(high) | 4(high) | 16(high) | business strategy plan/ meetings | enhance digital marketing & innovation skills | CMO | In progress | 15 days | 2025-04-14
R009 | Revenue loss due to fraud | Financial | Online transactions | Fraudulent transactions | 3(medium) | 5(critical) | 15(medium) | fraud detection system | Implement AI-based fraud monitoring | CFO | Open | 7 days | 2025-04-04
R010 | Phishing attack | cybersecurity/ Production | Employee emails | Social engineering | 4(high) | 5(critical) | 20(high) | security awareness training | simulated phishing tools | HR& IT | Mitigated | 24 hrs | 2025-03-31

## Risk Priortization
Risk description | Risk category | Risk score | Risk score | Risk description
Weak Password policy | Cybersecurity | 20(High) | 25(critical) | GDPR Non-compliance
Legacy system vulnerabilities | IT infrasructure | 10(Medium) | 20(high) | Phishing attack
System downtime | Operational | 12(medium) | 20(High) | Weak Password policy
GDPR Non-compliance | Compliance | 25(critical) | 16(high) | Competitor gaining market share
Negative media coverage | Reputational | 15(high) | 15(high) | Negative media coverage
Vendor data breach | Supply chain ( Third party risk) | 12(medium) | 15(medium) | Revenue loss due to fraud
Natural disaster affecting operations | Environmental | 5(low) | 12(medium) | Vendor data breach
Competitor gaining market share | Strategic | 16(high) | 12(medium) | System downtime
Revenue loss due to fraud | Financial | 15(medium) | 10(Medium) | Legacy system vulnerabilities
Phishing attack | cybersecurity/ Production | 20(high) | 5(low) | Natural disaster affecting operations

## Risk Treatment plan
Risk | Risk Level | Treatment Strategy | Action Plan | Responsible Person(Owner) | Resources Needed | Timeline | Monitor& Review
Phishing attack leading to data breach | High | Mitigation | Implement email security tools, conduct phishing training | IT Security Team | Security software, training budget | 3 months | Monthly security audits, phishing tests
Non compliance with GDPR | High | Tranfer/ Mitigation | Hire compliance expert, conduct annual GDPR audit | Compliance officer | Audit team, legal support | 6 months | quarterly review, annual compliance audit
Ransomware attack | Critical | Mitigation | Deploy endpoint protection, enforce regular backups | IT Security Manager | cybersecurity tools, backup infrastructure | 2 months | incident response drills, log monitoring
Server failure causing downtime | Medium | Acceptance | Maintaining backup, accept minimal downtime | IT Operations | cloud backup service | ongoing | monthly system health checks

## Types of Monitoring
S.No. | Type | Purpose | Example
1 | Risk monitoring | Track known and emerging risk | Updating risk register, reviewing tratment plan, conducting assessments
2 | Control Monitoring | Ensure internal controlss are working | Continuous Control Monitoring (CCM), Control testing
3 | Project Monitoring | Keep projects on track for time, cost and quality | Gantt charts, progress dashboards, milestone tracking
4 | Security Monitoring | Detect and respond to threats | SIEM tools(Splunk, IBM Qradar); log analysis
5 | Compliance Monitoring | Check adherence to laws/ regulations | Policy violations, compliance scorecards, access reviews
6 | Performance Monitoring | Assess business/ IT performance | Uptime monitoring, SLA Tracking, KPI dashboards